## Sheet1
PROJECT MEMBER | STUDENT CODE
Ngô Hoàn Tâm Huy (Leader) | CE140548
Ngô Nguyễn Hồng Hải Long | CE140007
Trần Ngọc Mẫn Huy | CE140289
Trần Hoàng Quí | CE140632
PROJECT NAME | START DATE | END DATE |  |  | OVERALL PROGRESS
Feast Egg Restaurant | 2021-05-31 | 2021-07-10 |  |  | 23%
TASK NAME | FEATURE DESCRIPTION | RESPONSIBLE | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1 |  |  | 2021-05-31 | 2021-06-04 | 4 | Complete
Login |  | T.Huy | 2021-05-31 | 2021-06-04 | 4 | Complete
Register |  | T.Huy | 2021-05-31 | 2021-06-04 | 4 | Complete
Server |  | Quí | 2021-05-31 | 2021-06-04 | 4 | Complete
Sprint 2 |  |  | 2021-06-11 | 2021-06-18 | 7 | In Progress
Reservation management | Customer create, update, delete reservation | Mẫn Huy, Quí | 2021-06-11 | 2021-06-18 | 7 | In Progress
Homepage | Home page, view menu, search | Long, T.Huy | 2021-06-11 | 2021-06-18 | 7 | In Progress
Sprint 3 |  |  | 2021-06-18 | 2021-06-25 | 7 | Not Started
Manage Account profile |  | T.Huy, Long | 2021-06-18 | 2021-06-25 | 7 | Not Started
Reservation management | Staff manage reservation | Mẫn Huy, Quí | 2021-06-18 | 2021-06-25 | 7 | Not Started
Sprint 4 |  |  | 2021-06-25 | 2021-07-02 | 7 | Not Started
Manage Menu |  | T.Huy, Long | 2021-06-25 | 2021-07-02 | 7 | Not Started
Manage Staff | Manager manage staff account | Mẫn Huy, Quí | 2021-06-25 | 2021-07-02 | 7 | Not Started
Sprint 5 |  |  | 2021-07-02 | 2021-07-09 | 7 | Not Started
Manage Discount (Customer) |  | T.Huy | 2021-07-02 | 2021-07-09 | 7 | Not Started
Manage Discount (Staff) |  | Long | 2021-07-02 | 2021-07-09 | 7 | Not Started
Manage balance |  | Mẫn Huy | 2021-07-02 | 2021-07-09 | 7 | Not Started
Manage points |  | Quí | 2021-07-02 | 2021-07-09 | 7 | Not Started